## Dashboard
AI Voice Bot Project - Task Tracker
6-Week Sprint Plan ¦ Python + Azure Agents + VoiceLive + React
OVERALL PROGRESS |  |  | SPRINT PROGRESS
Total Tasks | 48 |  | Sprint | Tasks | Done | Progress %
Completed | 0 |  | Week 1 | 8 | 0 | 0
In Progress | 0 |  | Week 2 | 8 | 0 | 0
Not Started | 48 |  | Week 3 | 8 | 0 | 0
Blocked | 0 |  | Week 4 | 8 | 0 | 0
Completion % | 0 |  | Week 5 | 8 | 0 | 0
|  |  | Week 6 | 8 | 0 | 0
BY CATEGORY |  |  | TEAM WORKLOAD
Category | Tasks | Done | Assignee | Assigned | Done | In Progress
Backend | 12 | 0 | Alex (Backend) | 0 | 0 | 0
Frontend | 7 | 0 | Jordan (Frontend) | 0 | 0 | 0
AI/ML | 8 | 0 | Sam (AI/ML) | 0 | 0 | 0
DevOps | 7 | 0 | Taylor (DevOps) | 1 | 0 | 0
Design | 2 | 0 | Morgan (QA) | 0 | 0 | 0
Testing | 8 | 0 | Casey (Design) | 0 | 0 | 0
Documentation | 4 | 0

## Tasks
ID | Sprint | Category | Task | Description | Assignee | Priority | Status | Start | Due | Notes
W1-01 | Week 1 | Documentation | Project architecture design | Define system components, data flow, integration points | Ravi | High | Not Started | 2025-01-13 | 2025-01-17
W1-02 | Week 1 | DevOps | Development environment setup | Docker, local dev configs, env variables | Surbhi/Shruti | High | Not Started | 2025-01-13 | 2025-01-15
W1-03 | Week 1 | DevOps | Git repository & branching strategy | Set up repo, branch protection, PR templates | Surbhi/Shruti | High | Not Started | 2025-01-14 | 2025-01-15
W1-04 | Week 1 | DevOps | CI/CD pipeline skeleton | GitHub Actions for build, test, deploy stages | Surbhi/Shruti | Medium | Not Started | 2025-01-15 | 2025-01-17
W1-05 | Week 1 | Backend | Database schema design | Design tables for users, sessions, conversations | Surbhi/Shruti | High | Not Started | 2025-01-14 | 2025-01-16
W1-06 | Week 1 | Documentation | API specification document | OpenAPI spec for all planned endpoints | Surbhi/Shruti | High | Not Started | 2025-01-15 | 2025-01-17
W1-07 | Week 1 | Frontend | React project initialization | Vite + React + TypeScript + TailwindCSS setup | Surbhi/Shruti | High | Not Started | 2025-01-13 | 2025-01-15
W1-08 | Week 1 | Backend | Python backend scaffolding | FastAPI project structure, config, health endpoints | Surbhi/Shruti | High | Not Started | 2025-01-13 | 2025-01-15
W2-01 | Week 2 | AI/ML | Azure Agent SDK setup | Configure Azure AI services, authentication, SDK | Surbhi/Shruti | High | Not Started | 2025-01-18 | 2025-01-21
W2-02 | Week 2 | AI/ML | VoiceLive API integration research | Evaluate API capabilities, rate limits, pricing | Surbhi/Shruti | High | Not Started | 2025-01-18 | 2025-01-20
W2-03 | Week 2 | Backend | Voice processing module | Audio format conversion, chunking, streaming | Surbhi/Shruti | High | Not Started | 2025-01-18 | 2025-01-22
W2-04 | Week 2 | Backend | Authentication service | JWT tokens, user sessions, API key management | Surbhi/Shruti | High | Not Started | 2025-01-18 | 2025-01-21
W2-05 | Week 2 | Backend | Core API endpoints | User, conversation, voice session endpoints | Surbhi/Shruti | High | Not Started | 2025-01-20 | 2025-01-22
W2-06 | Week 2 | Backend | Database models implementation | SQLAlchemy models, migrations, relationships | Surbhi/Shruti | Medium | Not Started | 2025-01-19 | 2025-01-21
W2-07 | Week 2 | Backend | Logging framework | Structured logging, request tracing, audit logs | Surbhi/Shruti | Medium | Not Started | 2025-01-20 | 2025-01-22
W2-08 | Week 2 | Backend | Error handling framework | Global exception handlers, error responses | Surbhi/Shruti | Medium | Not Started | 2025-01-21 | 2025-01-22
W3-01 | Week 3 | AI/ML | Azure OpenAI integration | GPT-4 API setup, prompt management, responses | Surbhi/Shruti | High | Not Started | 2025-01-23 | 2025-01-26
W3-02 | Week 3 | AI/ML | Speech-to-text pipeline | Real-time transcription via Azure Speech | Surbhi/Shruti | High | Not Started | 2025-01-23 | 2025-01-26
W3-03 | Week 3 | AI/ML | Text-to-speech pipeline | Natural voice synthesis, SSML support | Surbhi/Shruti | High | Not Started | 2025-01-24 | 2025-01-27
W3-04 | Week 3 | AI/ML | Conversation state management | Context tracking, conversation history, memory | Surbhi/Shruti | High | Not Started | 2025-01-25 | 2025-01-27
W3-05 | Week 3 | AI/ML | Agent prompt engineering | System prompts, few-shot examples, guardrails | Surbhi/Shruti | High | Not Started | 2025-01-25 | 2025-01-27
W3-06 | Week 3 | Backend | Voice bot core logic | Orchestration of STT -> LLM -> TTS pipeline | Surbhi/Shruti | High | Not Started | 2025-01-25 | 2025-01-27
W3-07 | Week 3 | AI/ML | Response generation module | Streaming responses, interruption handling | Surbhi/Shruti | Medium | Not Started | 2025-01-26 | 2025-01-27
W3-08 | Week 3 | Backend | Context memory system | Session-based and persistent memory storage | Surbhi/Shruti | Medium | Not Started | 2025-01-26 | 2025-01-27
W4-01 | Week 4 | Design | UI/UX mockups finalization | Figma designs for all screens, components | Kirti | High | Not Started | 2025-01-28 | 2025-01-30
W4-02 | Week 4 | Frontend | React component architecture | Atomic design structure, shared components | Kirti | High | Not Started | 2025-01-28 | 2025-01-30
W4-03 | Week 4 | Frontend | Voice interface component | Microphone controls, visual feedback, waveform | Kirti | High | Not Started | 2025-01-29 | 2025-02-01
W4-04 | Week 4 | Frontend | Real-time audio handling | WebRTC/WebSocket audio streaming | Kirti | High | Not Started | 2025-01-30 | 2025-02-01
W4-05 | Week 4 | Frontend | API integration layer | React Query, API client, error boundaries | Kirti | High | Not Started | 2025-01-30 | 2025-01-31
W4-06 | Week 4 | Frontend | State management setup | Zustand/Redux for global state | Kirti | Medium | Not Started | 2025-01-29 | 2025-01-30
W4-07 | Week 4 | Frontend | Chat interface UI | Message display, typing indicators, history | Kirti | Medium | Not Started | 2025-01-31 | 2025-02-01
W4-08 | Week 4 | Design | Settings & configuration UI | User preferences, voice settings, theme | Kirti | Low | Not Started | 2025-01-31 | 2025-02-01
W5-01 | Week 5 | Testing | Frontend-backend integration | Connect all React components to live APIs | Kirti | High | Not Started | 2025-02-02 | 2025-02-04
W5-02 | Week 5 | Testing | End-to-end testing | Playwright tests for critical user flows | Samya | High | Not Started | 2025-02-02 | 2025-02-05
W5-03 | Week 5 | Testing | Voice quality testing | Latency, accuracy, naturalness evaluation | Samya | High | Not Started | 2025-02-03 | 2025-02-05
W5-04 | Week 5 | Backend | Performance optimization | Database queries, caching, async processing | Surbhi | High | Not Started | 2025-02-03 | 2025-02-05
W5-05 | Week 5 | Testing | Security audit | OWASP checks, penetration testing, auth review | Taylor (DevOps) | High | Not Started | 2025-02-04 | 2025-02-06
W5-06 | Week 5 | Backend | Error handling improvements | Edge cases, graceful degradation | Shruti | Medium | Not Started | 2025-02-04 | 2025-02-05
W5-07 | Week 5 | Testing | User acceptance testing | Internal team testing, feedback collection | Samya | Medium | Not Started | 2025-02-05 | 2025-02-06
W5-08 | Week 5 | Testing | Bug fixes sprint | Address issues from testing phase | Shruti | High | Not Started | 2025-02-05 | 2025-02-06
W6-01 | Week 6 | DevOps | Production environment setup | Cloud infrastructure, networking, secrets | Shruti | High | Not Started | 2025-02-07 | 2025-02-09
W6-02 | Week 6 | DevOps | Security hardening | SSL, WAF, rate limiting, DDoS protection | Shruti | High | Not Started | 2025-02-07 | 2025-02-09
W6-03 | Week 6 | Testing | Load testing | Stress test concurrent users, find bottlenecks | Samya | High | Not Started | 2025-02-08 | 2025-02-10
W6-04 | Week 6 | Documentation | Technical documentation | API docs, architecture docs, runbooks | Shruti | High | Not Started | 2025-02-08 | 2025-02-10
W6-05 | Week 6 | DevOps | Monitoring & alerting setup | Prometheus, Grafana, PagerDuty integration | Shruti | High | Not Started | 2025-02-09 | 2025-02-10
W6-06 | Week 6 | DevOps | Final deployment | Blue-green deployment to production | Shruti | High | Not Started | 2025-02-10 | 2025-02-11
W6-07 | Week 6 | Documentation | User documentation | User guides, FAQ, troubleshooting | Shruti | Medium | Not Started | 2025-02-09 | 2025-02-11
W6-08 | Week 6 | Testing | Post-launch monitoring | Watch metrics, respond to issues, hotfixes | Samya | High | Not Started | 2025-02-11 | 2025-02-11

## Reference
Status Options | Priority | Categories | Team | HOW TO USE
Not Started | High | Backend | Surbhi/Shruti | 1. Update Status in column H as tasks progress
In Progress | Medium | Frontend | Surbhi | 2. Dashboard formulas update automatically
Blocked | Low | AI/ML | Surbhi/Shruti | 3. Colors indicate: Green=Done, Yellow=In Progress, Red=Blocked, Gray=Not Started
Done |  | DevOps | Taylor (DevOps) | 4. Filter Tasks sheet by Sprint, Category, or Assignee
|  | Design | Kirti | 5. Add notes in column K for context
|  | Testing | Samya | 6. Team members can filter by their name to see assignments
|  | Documentation | Shruti